## Sheet1
Date | Time | Members | Description of Activity
2019-09-25 | 9:00 | Siddarth, Siddharth | Began work on the grammar rules (phase 2, step 1), finished batch 0 and batch 1
2019-09-25 | 14:00 | Thomas, Siddarth, Siddharth, Shawn | Fixed batch 1, began work on batch 2
2019-09-25 | 15:00 | Siddarth, Siddharth, Shawn | Worked on and finished batch 2, 3, and 4; we are now ready for phase 2 step 2
2019-09-26 | 20:00 | Thomas, Siddarth, Siddharth, Shawn | Set up the ANTLR4 listener (phase 2, step 2, part 1)
2019-09-28 | 20:30 | Thomas, Siddarth, Siddharth, Shawn | Worked to understand what we need to do to complete phase 2
2019-09-29 | 19:30 | Thomas, Siddarth, Siddharth, Shawn | Fixed an error in the grammar rules in batch 3 and 4
2019-09-29 | 20:00 | Thomas, Siddarth, Siddharth, Shawn | Set up the ANTLR4 listener again to account for the grammar rule change
2019-09-29 | 22:30 | Siddarth, Siddharth | Began work overriding the methods in MyRulesBaseListener
2019-09-29 | 22:30 | Thomas, Shawn | Developed the DBMS structure
2019-09-30 | 10:00 | Siddarth | Developed a getLeafNodes function to easily get the leaves
2019-09-30 | 18:00 | Thomas, Shawn | Created the DBMS structure, began work on developing necessary methods in DBMS class
2019-09-30 | 18:30 | Siddarth | Implemented Dijkstra's Shunting Algorithm for Conditions
2019-09-30 | 20:00 | Siddharth | Implemented Dijkstra's Shunting Algorithm for Atomic Expressions
2019-09-30 | 21:30 | Thomas, Shawn | Created and tested the create, insert, and union methods
2019-10-02 | 9:22 | Siddarth | Connected the listener with the DBMS; made CREATE, INSERT and SHOW to work properly with the listener class
2019-10-04 | 13:00 | Thomas, Shawn | Created helper function in DBMS to find index of tables
2019-10-04 | 16:00 | Thomas, Shawn | Found and fixed logic errors in various methods in DBMS
2019-10-04 | 19:00 | Thomas, Shawn | Refactored existing DBMS functions to be more simplified and easier to read by using Java's inbuilt functions
2019-10-04 | 18:00 | Siddarth, Siddharth | Finished making the nested union commands work by modifying Dijkstra's Algorithm code
2019-10-04 | 21:00 | Siddarth, Siddharth | Finished nested select statement and nested product statements
2019-10-04 | 22:30 | Thomas, Shawn | Created more DBMS methods
2019-10-06 | 0:30 | Thomas | Created more DBMS methods
2019-10-06 | 23:00 | Thomas | Finished the last of the needed methods in the DBMS
2019-10-07 | 3:00 | Siddarth, Siddharth | Created some helper DBMS functions, edited existing DBMS methods
2019-10-10 | 15:00 | Siddarth | Found the last coding mistake in phase 2, debugged the code
2019-10-14 | 18:30 | Siddharth | Began work on the a basic GUI using Scene Builder
2019-10-14 | 22:30 | Thomas, Shawn | Designed and finished up a GUI complete with changing scenes
2019-10-14 | 23:00 | Siddarth | Made query 4 work for the single credits JSON
2019-10-15 | 16:00 | Thomas, Shawn, Siddharth | Moved JavaFX GUI into main Java Project. Fixed additional bugs that occured with transfer.
2019-10-17 | 11:00 | Siddarth, Siddharth | Implemented query 3 and query 4 in the GUI
2019-10-17 | 17:00 | Thomas, Siddharth | Rebuilt query 3 to use SQL
2019-10-17 | 18:30 | Thomas, Siddharth | Finished and implemented query 2 in the GUI
2019-10-17 | 20:30 | Thomas, Siddharth | Made the input consistent with the grammar we have (i.e. normalizing the input) - project is ready for submission
2019-10-18 | 16:00 | Thomas | Merged branches back to master